## Requirements Inventory
Goal ID | SMART Goal | Requirement ID | Requirement Statement | Transaction (Input → Process → Output) | Type | Priority | Status Percentage | Notes / Issues | Owner
G1 | Sustain active cognitive engagement among Grade 8–9 students during continuous 30-minute gameplay sessions, measured by an idle rate < 15% in the Elemental Resonance puzzle module. | REQ-101 | The system shall provide an interactive canvas workbench where students drag and drop element tiles to synthesize compounds that clear environmental obstacles (FR-1.1). | Student drags element tiles onto the reaction zone and clicks Synthesize → System validates the combination against curriculum rules (ValidationService) → Valid: Elemental Resonance animation clears the obstacle and unlocks the path; invalid: handled by REQ-102. | Functional | Must | 90% | Inherited MVP feature, retained. Verified by TC-02 (POST /api/features/domain-interaction/synthesize returns UNLOCK_PATH). | Benolirao, Ceniza
G1 | Sustain active cognitive engagement among Grade 8–9 students during continuous 30-minute gameplay sessions, measured by an idle rate < 15% in the Elemental Resonance puzzle module. | REQ-102 | The system shall evaluate an invalid combination against a chemical property library and display a contextual 'Meaningful Byproduct' alert instead of a generic 'Wrong' notice (FR-1.2). | Student submits an invalid combination → System queries the feedback library (falls back to a general periodic group/period principle) and records the failed attempt → Student sees a chemistry-based micro-lesson alert; selected tiles are preserved. | Functional | Must | 95% | Validated well in MVP (91.4% byproduct recovery). Verified by TC-03. | Benolirao, Ceniza
G1 | Sustain active cognitive engagement among Grade 8–9 students during continuous 30-minute gameplay sessions, measured by an idle rate < 15% in the Elemental Resonance puzzle module. | REQ-103 | The system shall activate the Hazmat Protocol after 5 or more failed attempts within a 15-second sliding window, graying out and locking element tiles not on the target solution path (FR-1.3). | Student makes 5+ failed combinations within 15 s → Sliding-window service raises the Hazmat flag → Non-solution tiles are disabled (opacity 35%, pointer-events none) and a volatility banner shows; lifted on the next valid synthesis. | Functional | Must | 95% | INC-002 (400 ms frame drop on mobile) resolved by element-level styles in ElementTile.jsx. Verified by TC-04. | Benolirao, Ceniza
G1 | Sustain active cognitive engagement among Grade 8–9 students during continuous 30-minute gameplay sessions, measured by an idle rate < 15% in the Elemental Resonance puzzle module. | REQ-104 | The system shall partition each domain into three sequential stages and lock advanced rooms until prerequisite reactions are completed (minimum 3 correct reactions) (FR-1.4). | Student selects a locked room/stage → System checks prerequisite completions (ProgressionValidationService) → Access denied with 'Chamber is Sealed' prompt, or unlocked when prerequisites are met; progress is persisted. | Functional | Must | 90% | Verified by TC-05 (Domain 3 blocked for a new user, unlocked after 3 reactions). | Benolirao, Ceniza
G1 | Sustain active cognitive engagement among Grade 8–9 students during continuous 30-minute gameplay sessions, measured by an idle rate < 15% in the Elemental Resonance puzzle module. | REQ-105 | The system shall randomize target compound assignments from the reaction pool at the start of each session without repeating completed challenges (FR-1.5). | Student enters a Domain → System fetches the pool, excludes compounds already completed this session, and reshuffles → Student receives a fresh, non-repeating challenge set. | Functional | Should | 90% | Prevents rote memorization. Verified by TC-06. | Benolirao, Ceniza
G2 | Demonstrate alignment with DepEd Grade 8–9 Chemical Bonding competencies by achieving a normalized learning gain g ≥ 0.40 (target ≥ 0.50) and ≥ 75% post-test mastery benchmark. | REQ-201 | The system shall render a Stage Debrief at the clearance of Stage 1 and Stage 2, showing Doctor Atom's evaluation, the bonding masteries unlocked, and a blueprint preview of the next stage; the learner must click 'Dive Deeper to Stage {X}' to proceed (FR-1.6). | Student clears a stage barrier → System pauses the canvas and opens StageTransitionModal with the mastery checklist and next-stage blueprint → Student confirms and the next stage inventory/obstacle loads. | Functional | Must | 80% | NEW from MVP Finding #1 / Refactoring Priority #1 (FR-1.6). Fully implemented in StageTransitionModal.jsx; displays Doctor Atom commentary, unlocked masteries, and next blueprint. Verified by TC-07. | Ceniza, Ocampo
G2 | Demonstrate alignment with DepEd Grade 8–9 Chemical Bonding competencies by achieving a normalized learning gain g ≥ 0.40 (target ≥ 0.50) and ≥ 75% post-test mastery benchmark. | REQ-202 | The system shall render a Domain Completion Debrief after Stage 3, showing overall accuracy %, elapsed time, all 12 synthesized compounds with formulas, and a review of the core bonding concept mastered (FR-1.6). | Student clears Stage 3 → System aggregates accuracy, time and compound list (ProgressionService) → DebriefingModal displays the mission summary and routes the student to the Hub or replay. | Functional | Must | 80% | NEW from MVP Finding #1 / Refactoring Priority #1. Covers educational bonding content rendered in StageTransitionModal.jsx and DebriefingModal.jsx. Verified by TC-07. | Ceniza, Ocampo
G2 | Demonstrate alignment with DepEd Grade 8–9 Chemical Bonding competencies by achieving a normalized learning gain g ≥ 0.40 (target ≥ 0.50) and ≥ 75% post-test mastery benchmark. | REQ-203 | The system shall reinforce chemical bonding theory by displaying the formula, bond classification (polar/nonpolar covalent vs. ionic), Lewis electron-dot recap, and real-world application within the milestone debrief modals (FR-1.6). | Student clears a stage or domain barrier → System compiles stoichiometric properties and bonding classification rules (ProgressionService / FeedbackLibraryService) → Debrief modal renders visual Lewis structures and real-world utility lessons before advancing. | Functional | Must | 80% | NEW from MVP Finding #1 / Refactoring Priority #1 (FR-1.6). Evaluates conceptual bonding content in StageTransitionModal.jsx and DebriefingModal.jsx. Verified by TC-07. | Ceniza, Ocampo
G2 | Demonstrate alignment with DepEd Grade 8–9 Chemical Bonding competencies by achieving a normalized learning gain g ≥ 0.40 (target ≥ 0.50) and ≥ 75% post-test mastery benchmark. | REQ-204 | The client shall serialize the Pre-Test score, total, percentage and choices into JSON and send an asynchronous HTTPS POST to /api/telemetry/pretest to persist the baseline in Supabase, keeping localStorage as an offline fallback (FR-2.4). | Student submits the 3-item pre-test → Client builds the JSON payload and POSTs it to /api/telemetry/pretest; server commits record to PRETEST_DIAGNOSTIC (HTTP 201) → Baseline stored in cloud; offline fallback stored in localStorage. | Functional | Must | 70% | NEW from MVP Finding #2 (12/30 baselines lost to cache resets). Verified by TC-11 (201 Created in 380 ms; offline queue works). Also supports G4 (< 2 s cloud persistence). | Benolirao, Dibdib
G3 | Establish 1v1 matchmaking connections in < 5 seconds and determine Speed-to-Compound victory outcomes with 100% computational fairness under network latency constraints. | REQ-301 | The system shall generate a unique 5-digit alphanumeric room access code and connect two players via Supabase Realtime in under 5 seconds (FR-3.1). | Host creates a room; guest enters the code and nickname → System validates the code server-side and opens the Realtime channel → Both players enter the pre-match lobby; invalid code shows 'room not found'. | Functional | Must | 85% | Verified by TC-12 (lobby established in 1.45 s vs 5.0 s target). | Dibdib, Ceniza
G3 | Establish 1v1 matchmaking connections in < 5 seconds and determine Speed-to-Compound victory outcomes with 100% computational fairness under network latency constraints. | REQ-302 | Once a match starts, the system shall broadcast an identical compound challenge and element inventory to both players with a synchronized 3-second countdown (FR-3.2). | Host starts the match → System selects one challenge and broadcasts it via Supabase Realtime → Both players see the same target; controls stay locked during the 3 s countdown, then unlock together. | Functional | Must | 90% | Verified by TC-13. | Dibdib, Benolirao
G3 | Establish 1v1 matchmaking connections in < 5 seconds and determine Speed-to-Compound victory outcomes with 100% computational fairness under network latency constraints. | REQ-303 | The system shall evaluate completion timestamps and reaction-path efficiency server-side to determine the match winner with 100% accuracy, breaking ties by fewer failed attempts (FR-3.3). | First player sends a 'solved' packet → Referee compares timestamps/efficiency and locks the opponent → Victory/Defeat banners are shown and the result is saved to Supabase. | Functional | Must | 85% | INC-003 (double victory animation within 50 ms) resolved by removing optimistic client victory. Verified by TC-14. | Benolirao, Dibdib
G3 | Establish 1v1 matchmaking connections in < 5 seconds and determine Speed-to-Compound victory outcomes with 100% computational fairness under network latency constraints. | REQ-304 | The system shall consolidate multiplayer match results (win/loss) and Speed-to-Compound efficiency into the student's mastery profile, handling duplicate submissions idempotently (FR-2.3). | Match concludes → System retrieves the player's proficiency, recalculates the rating (ELO) and stores it in Supabase → Updated rating is reflected in the Mastery Dashboard. | Functional | Must | 85% | Verified by TC-10 (+25 / −20; duplicate payload ignored). | Benolirao, Dibdib
G4 | Achieve an average satisfaction score ≥ 4.2/5.0 on the Mastery Dashboard and Speed-to-Compound mechanics, with session telemetry persisted to Supabase in < 2 seconds. | REQ-401 | The system shall calculate accuracy and completion time upon room clearance and commit the performance record to Supabase in under 2 seconds, showing a friendly error if the write fails (FR-2.1). | Student clears a Domain → Telemetry hook aggregates metrics and dispatches them to the backend → Record is stored under the session nickname in < 2 s (482 ms measured); UI moves on to the dashboard/next Domain. | Functional | Must | 90% | INC-001 (duplicate records on reconnect) resolved with sync_transaction_id upsert. Verified by TC-08. | Benolirao, Dibdib
G4 | Achieve an average satisfaction score ≥ 4.2/5.0 on the Mastery Dashboard and Speed-to-Compound mechanics, with session telemetry persisted to Supabase in < 2 seconds. | REQ-402 | The system shall render a Mastery Dashboard showing accuracy, completion speed and weak bonding areas per domain, within 3 seconds of access (FR-2.2). | Student opens the dashboard → System queries historical sessions and aggregates per-domain metrics → Scatter plot shows results; domains < 60% accuracy are flagged red; blank-slate prompt if no data. | Functional | Must | 85% | Verified by TC-09. | Ceniza
G4 | Achieve an average satisfaction score ≥ 4.2/5.0 on the Mastery Dashboard and Speed-to-Compound mechanics, with session telemetry persisted to Supabase in < 2 seconds. | REQ-403 | The system shall send WebSocket heartbeat pings every 3 seconds during active matches; if a peer is silent for more than 8 seconds it shall pause the match timer and show a reconnecting state, and if reconnection fails after 15 seconds it shall award a forfeit victory to the connected player without corrupting records (FR-3.4). | Heartbeat ping every 3 s → Silence detector trips at 8 s: timer pauses and 'Opponent Disconnected' modal (15 s) shows → On timeout the referee records FORFEIT_WIN and returns the player to results/lobby. | Functional | Must | 60% | NEW from MVP Finding #3 (3 of 18 matches froze; satisfaction 3.82/5). Verified by TC-15 (pause at 8.15 s, forfeit at 15.0 s). | Dibdib, Benolirao
G4 | Achieve an average satisfaction score ≥ 4.2/5.0 on the Mastery Dashboard and Speed-to-Compound mechanics, with session telemetry persisted to Supabase in < 2 seconds. | REQ-404 | The system shall let students start a session with only a self-assigned nickname — no registration, authentication or PII (zero-registration onboarding). | Student enters a nickname at the NicknameGate → System stores it in localStorage and calls /api/users/login → Student reaches the Dashboard Hub in < 1 s with the nickname shown. | Functional | Must | 95% | Core design constraint. No dedicated SDD section — add a short note if required. Verified by TC-01 (320 ms). | Benolirao, Dibdib
G4 | Achieve an average satisfaction score ≥ 4.2/5.0 on the Mastery Dashboard and Speed-to-Compound mechanics, with session telemetry persisted to Supabase in < 2 seconds. | REQ-405 | The interface shall enforce a minimum 48 px × 48 px touch target for all element tiles and action buttons on 360–768 px viewports, with no horizontal overflow (NFR-USA-01). | Student taps/drags tiles on a phone/tablet → UI applies 48 px bounding boxes, 8 px margins and touch-action: none → Accurate selection with no page scroll or mis-click. | Non-functional | Must | 90% | NEW from validation (mobile mis-clicks). Verified by TC-16 (tiles measured 52 px; 0 mistaps). | Ceniza, Erica Dabalos
G4 | Achieve an average satisfaction score ≥ 4.2/5.0 on the Mastery Dashboard and Speed-to-Compound mechanics, with session telemetry persisted to Supabase in < 2 seconds. | REQ-406 | The system shall store telemetry and pre-test payloads in an offline FIFO queue in localStorage during network loss and auto-flush them to Supabase on reconnection (NFR-REL-01). | Network drops during a room clear or pre-test → Payload (with syncTransactionId) is queued in elementopia_sync_queue → On the 'online' event the queue flushes via POST and empties, with no duplicate rows. | Non-functional | Must | 60% | NEW from MVP Finding #2; shares INC-001 fix. Verified by TC-17. | Dibdib, Benolirao
G4 | Achieve an average satisfaction score ≥ 4.2/5.0 on the Mastery Dashboard and Speed-to-Compound mechanics, with session telemetry persisted to Supabase in < 2 seconds. | REQ-407 | The system shall keep canvas drag-and-drop response under 16 ms (60 FPS) and complete cloud writes in under 2 seconds (NFR-PERF-01). | Student drags tiles continuously and triggers synthesis → Canvas renders at ≥ 58 FPS under 4× CPU slowdown → Smooth interaction; session write < 2 s. | Non-functional | Must | 90% | Verified by TC-18 (59.4 FPS avg; 14.2 ms peak; 482 ms write). SRS bullet has no ID; STD labels it NFRPERF-01 — standardize to NFR-PERF-01. | Ceniza, Benolirao
G4 | Achieve an average satisfaction score ≥ 4.2/5.0 on the Mastery Dashboard and Speed-to-Compound mechanics, with session telemetry persisted to Supabase in < 2 seconds. | REQ-408 | The system shall collect no PII, encrypt all channels (HTTPS/TLS 1.3, WSS) and validate chemistry rules and access codes server-side (NFR-SEC-01). | Client submits nickname/validation request → Backend enforces TLS, stores no identity fields, and re-evaluates stoichiometry server-side → Forged 'valid' claims are rejected (HTTP 400/INVALID). | Non-functional | Must | 95% | Supports RA 10173 compliance (SPMP). Verified by TC-19. | Ocampo, Benolirao
Note: | REQ-101 (Goal#¦Transaction#)

## Requirements Traceability Matri
Requirement ID | SRS Reference (Use Cases, Activity Diagrams, Wireframes) | SDD Reference (Class Diagrams, Sequence Diagrams, User Interfaces, Databases) | Implementation Module(s)/Component(s) | STD Reference (Test Case IDs) | Status
REQ-101 | UC-101 (SRS p.12), AD-101 (p.13), WF-101 (p.14) — SRS §3.2 FR-1.1 | CD-101, SD-101, UI-101, DB-101 — SDD §3.1.1 (pp.10–12) | ElementalDomainCanvas.jsx, ActiveInventoryTray.jsx, ReactionController.java, ValidationService.java, TelemetryService.java | TC-02 | Passed
REQ-102 | UC-102 (SRS p.15), AD-102 (p.16), WF-102 (p.17) — SRS §3.2 FR-1.2 | CD-102, SD-102, UI-102, DB-102 — SDD §3.1.2 (pp.13–17) | DiagnosticAlertOverlay.jsx, FeedbackLibraryContext.jsx, DiagnosticController.java, FeedbackLibraryService.java, IncidentCounterService.java | TC-03 | Passed
REQ-103 | UC-103 (SRS p.18), AD-103 (p.19), WF-103 (p.20) — SRS §3.2 FR-1.3 | CD-103, SD-103, UI-103, DB-103 — SDD §3.1.3 (pp.17–20) | HazmatOverlayController.jsx, SystemVolatilityBanner.jsx, FailsafeMonitorController.java, SlidingWindowEvaluationService.java, FailsafeTelemetryService.java | TC-04 | Passed
REQ-104 | UC-104 (SRS p.21), AD-104 (p.22), WF-104 (p.23) — SRS §3.2 FR-1.4 | CD-104, SD-104, UI-104, DB-104 — SDD §3.1.4 (pp.21–25) | RoomSelectionDashboard.jsx, ProgressionMapNode.jsx, ProgressionController.java, ProgressionValidationService.java, ProgressionTelemetryService.java | TC-05 | Passed
REQ-105 | UC-105 (SRS p.24), AD-105 (p.25), WF-105 (p.26) — SRS §3.2 FR-1.5 | CD-105, SD-105, UI-105, DB-105 — SDD §3.1.5 (pp.26–28) | DomainSessionManager, PuzzleStageRenderer, ChallengeController, ChallengeRandomizerService | TC-06 | Passed
REQ-201 | UC-201 (SRS p.27), AD-201 (p.28), WF-201 (p.29) — SRS §3.2 FR-1.6 | CD-201, SD-201, UI-201, DB-201 — SDD §3.1.6 (pp.29–32) | StageTransitionModal.jsx, ReactionController.java, ProgressionService.java | TC-07 | Passed
REQ-202 | UC-202 (SRS p.27), AD-202 (p.28), WF-202 (p.29) — SRS §3.2 FR-1.6 | CD-202, SD-202, UI-202, DB-202 — SDD §3.1.6 (pp.29–32) | DebriefingModal.jsx, ProgressionService.java | TC-07 | Passed
REQ-203 | UC-201, AD-201, WF-201 — SRS §3.2 FR-1.6 | CD-201, SD-201, UI-201/UI-202, DB-201 — SDD §3.1.6 (pp.29–32) | StageTransitionModal.jsx, DebriefingModal.jsx, FeedbackLibraryService.java | TC-07 | Passed
REQ-204 | UC-204 (SRS p.37), AD-204 (pp.38–39), WF-204 (p.40) — SRS §3.2 FR-2.4 | CD-204, SD-204, UI-204, DB-204 — SDD §3.2.4 (pp.43–45) | PreTestModal.jsx, PreTestSyncDispatcher.js, PreTestTelemetryController.java, PreTestPersistenceService.java, PRETEST_DIAGNOSTIC table | TC-11 | Passed
REQ-301 | UC-301 (SRS p.41), AD-301 (p.42), WF-301 (p.43) — SRS §3.2 FR-3.1 | CD-301, SD-301, UI-301, DB-301 — SDD §3.3.1 (pp.46–47) | MatchmakingController, CodeInputModal, RoomManagerService | TC-12 | Passed
REQ-302 | UC-302 (SRS p.44), AD-302 (p.45), WF-302 (p.46) — SRS §3.2 FR-3.2 | CD-302, SD-302, UI-302, DB-302 — SDD §3.3.2 (pp.48–50) | CompetitivePuzzleBoard, CountdownOverlay, TaskGeneratorService | TC-13 | Passed
REQ-303 | UC-303 (SRS p.47), AD-303 (p.48), WF-303 (p.49) — SRS §3.2 FR-3.3 | CD-303, SD-303, UI-303, DB-303 — SDD §3.3.3 (pp.51–53) | SpeedEvaluatorClient, MatchResultBanner, MatchRefereeService.java, MatchSyncController.java | TC-14 | Passed
REQ-304 | UC-304 (SRS p.35), AD-304 (p.36), WF-304 (p.37) — SRS §3.2 FR-2.3 | CD-304, SD-304, DB-304 — SDD §3.2.3 (pp.40–42); no UI | MatchConsolidationController, ProficiencyRecalculationService | TC-10 | Passed
REQ-401 | UC-401 (SRS p.30), AD-401 (p.31), WF-401 (p.32) — SRS §3.2 FR-2.1 | CD-401, SD-401, UI-401, DB-401 — SDD §3.2.1 (pp.33–35) | TelemetryCaptureHook, SessionDataDispatcher.js, AnalyticsController, TelemetryLoggingService.java | TC-08, TC-18 | Passed
REQ-402 | UC-402 (SRS p.32), AD-402 (p.33), WF-402 (p.34) — SRS §3.2 FR-2.2 | CD-402, SD-402, UI-402, DB-402 — SDD §3.2.2 (pp.36–39) | MasteryDashboardView, PerformanceScatterPlot, MasteryDashboardController, MasteryAggregationService | TC-09 | Passed
REQ-403 | UC-403, AD-403, WF-403 — SRS §3.2 FR-3.4 | CD-403, SD-403, UI-403, DB-403 — SDD §3.3.4 | HeartbeatTimeoutHandler.js, DisconnectRecoveryModal.jsx, MatchRefereeService.java | TC-15 | Passed
REQ-404 | SRS §1.2 Scope; §3.4 Usability | SDD §2.1 System Overview (p.8) — no dedicated diagram | NicknameGate, UserService.jsx, /api/users/login | TC-01 | Passed
REQ-405 | SRS §3.1.1; §3.4 Usability (NFR-USA-01) | SDD §4.1 (User Interface Design & Touch Targets) | ElementTile.jsx, ActiveInventoryTray.jsx, GameBoard.jsx, responsive CSS grid | TC-16 | Passed
REQ-406 | SRS §3.4 Reliability (NFR-REL-01) | SDD §4.2 (Offline Data Resilience & Telemetry Sync) | OfflineSyncManager (elementopia_sync_queue), SessionDataDispatcher.js, PreTestSyncDispatcher.js | TC-17 | Passed
REQ-407 | SRS §3.4 Performance (NFR-PERF-01) | SDD §2.2 Technology Stack (p.8) | GameBoard.jsx / ElementalDomainCanvas.jsx render loop, TelemetryLoggingService.java | TC-18 | Passed
REQ-408 | SRS §3.1.3; §3.4 Security (NFR-SEC-01) | SDD §2.1–2.3 (pp.8–9) | ValidationService.java, HTTPS/WSS configuration, Supabase schema (no PII columns) | TC-19 | Passed